## Data_Overview
Timestamp | Divisi | PIC | Jenis Update | Ada Isu | Kategori Isu | Prioritas Isu | Email Address
2026-06-01 09:00 | Digital Marketing | Wulan K. | Weekly Update | Ada | Budget & Finance | Low | wulan81@example-fsj.com
2026-06-01 10:00 | PR & Project Execution | Kayla P. | Weekly Update | Tidak Ada | - | - | kayla58@example-fsj.com
2026-06-01 17:00 | Sustainability (ESG) | Fajar M. | Weekly Update | Tidak Ada | - | - | fajar58@example-fsj.com
2026-06-02 17:00 | Visual Brand Creative | Dimas K. | Weekly Update | Tidak Ada | - | - | dimas53@example-fsj.com
2026-06-03 12:00 | Administration & Performance Reporting | Arka W. | Weekly Update | Tidak Ada | - | - | arka84@example-fsj.com
2026-06-03 16:00 | Program Management Officer (PMO) | Reza S. | Weekly Update | Tidak Ada | - | - | reza58@example-fsj.com
2026-06-03 17:00 | Human Resource | Aldo M. | Weekly Update | Tidak Ada | - | - | aldo82@example-fsj.com
2026-06-04 10:00 | Product & Website UI/UX (Website) | Kayla W. | Weekly Update | Tidak Ada | - | - | kayla92@example-fsj.com
2026-06-04 11:00 | Program Management Officer (PMO) | Intan W. | Monthly Update | - | - | - | intan98@example-fsj.com
2026-06-04 11:00 | Program Management Officer (PMO) | Fajar M. | Ad Hoc Document Submission | - | - | - | fajar33@example-fsj.com
2026-06-04 15:00 | Product & Website UI/UX (Product) | Reza K. | Weekly Update | Tidak Ada | - | - | reza97@example-fsj.com
2026-06-05 12:00 | Program Management Officer (PMO) | Reza A. | Quick Link & Asset Submission | - | - | - | reza93@example-fsj.com
2026-06-05 16:00 | Product & Website UI/UX (Product) | Fajar R. | Monthly Update | - | - | - | fajar63@example-fsj.com
2026-06-06 12:00 | Digital Marketing | Intan R. | Quick Link & Asset Submission | - | - | - | intan75@example-fsj.com
2026-06-07 12:00 | Administration & Performance Reporting | Gilang H. | Quick Link & Asset Submission | - | - | - | gilang18@example-fsj.com
2026-06-08 09:00 | Sustainability (ESG) | Wulan A. | Monthly Update | - | - | - | wulan32@example-fsj.com
2026-06-09 15:00 | Product & Website UI/UX (Website) | Intan R. | Monthly Update | - | - | - | intan10@example-fsj.com
2026-06-13 17:00 | Human Resource | Dian H. | Monthly Update | - | - | - | dian62@example-fsj.com
2026-06-15 10:00 | Visual Brand Creative | Aldo R. | Monthly Update | - | - | - | aldo90@example-fsj.com
2026-06-15 14:00 | Visual Brand Creative | Arka A. | Weekly Update | Ada | IT & Technical | High | arka26@example-fsj.com
2026-06-15 16:00 | Administration & Performance Reporting | Bima A. | Monthly Update | - | - | - | bima90@example-fsj.com
2026-06-16 12:00 | Product & Website UI/UX (Website) | Fajar K. | Weekly Update | Tidak Ada | - | - | fajar77@example-fsj.com
2026-06-16 15:00 | Product & Website UI/UX (Product) | Rafi S. | Weekly Update | Tidak Ada | - | - | rafi72@example-fsj.com
2026-06-16 16:00 | PR & Project Execution | Ilham S. | Weekly Update | Tidak Ada | - | - | ilham76@example-fsj.com
2026-06-17 10:00 | Digital Marketing | Fajar W. | Weekly Update | Ada | Legal & Contract | High | fajar77@example-fsj.com
2026-06-18 10:00 | Sustainability (ESG) | Aldo K. | Weekly Update | Ada | Legal & Contract | Medium | aldo19@example-fsj.com
2026-06-18 12:00 | Administration & Performance Reporting | Salsa H. | Weekly Update | Tidak Ada | - | - | salsa71@example-fsj.com
2026-06-18 16:00 | Human Resource | Rafi P. | Weekly Update | Ada | Budget & Finance | High | rafi45@example-fsj.com
2026-06-19 09:00 | Digital Marketing | Gilang P. | Monthly Update | - | - | - | gilang36@example-fsj.com
2026-06-19 12:00 | Program Management Officer (PMO) | Wulan H. | Weekly Update | Ada | Procurement & Vendor | Critical | wulan64@example-fsj.com
2026-06-19 12:00 | Visual Brand Creative | Salsa S. | Event / Program Execution | - | - | - | salsa90@example-fsj.com
2026-06-20 13:00 | PR & Project Execution | Putri P. | Monthly Update | - | - | - | putri69@example-fsj.com
2026-06-20 17:00 | Product & Website UI/UX (Website) | Dimas P. | Quick Link & Asset Submission | - | - | - | dimas46@example-fsj.com
2026-06-22 10:00 | Product & Website UI/UX (Website) | Bima K. | Ad Hoc Document Submission | - | - | - | bima92@example-fsj.com
2026-06-22 16:00 | Human Resource | Salsa W. | Ad Hoc Document Submission | - | - | - | salsa65@example-fsj.com
2026-06-27 13:00 | Sustainability (ESG) | Nadia R. | Ad Hoc Document Submission | - | - | - | nadia25@example-fsj.com
2026-06-28 11:00 | Product & Website UI/UX (Product) | Aldo P. | Ad Hoc Document Submission | - | - | - | aldo57@example-fsj.com
2026-06-29 09:00 | Human Resource | Bima M. | Quick Link & Asset Submission | - | - | - | bima28@example-fsj.com
2026-06-30 09:00 | Digital Marketing | Zahra P. | Weekly Update | Tidak Ada | - | - | zahra15@example-fsj.com
2026-06-30 17:00 | Administration & Performance Reporting | Rafi M. | Weekly Update | Tidak Ada | - | - | rafi15@example-fsj.com
2026-07-01 09:00 | Human Resource | Dian M. | Weekly Update | Tidak Ada | - | - | dian98@example-fsj.com
2026-07-01 11:00 | Visual Brand Creative | Dimas S. | Monthly Update | - | - | - | dimas19@example-fsj.com
2026-07-01 12:00 | Product & Website UI/UX (Product) | Aldo P. | Weekly Update | Tidak Ada | - | - | aldo52@example-fsj.com
2026-07-01 13:00 | Sustainability (ESG) | Yoga H. | Weekly Update | Tidak Ada | - | - | yoga23@example-fsj.com
2026-07-02 12:00 | Product & Website UI/UX (Website) | Wulan S. | Weekly Update | Tidak Ada | - | - | wulan68@example-fsj.com
2026-07-02 13:00 | Sustainability (ESG) | Reza M. | Monthly Update | - | - | - | reza65@example-fsj.com
2026-07-02 14:00 | PR & Project Execution | Salsa A. | Weekly Update | Tidak Ada | - | - | salsa41@example-fsj.com
2026-07-02 14:00 | Product & Website UI/UX (Product) | Nadia P. | Monthly Update | - | - | - | nadia47@example-fsj.com
2026-07-02 16:00 | Administration & Performance Reporting | Fajar K. | Monthly Update | - | - | - | fajar87@example-fsj.com
2026-07-02 16:00 | Product & Website UI/UX (Product) | Dimas M. | Event / Program Execution | - | - | - | dimas96@example-fsj.com
2026-07-03 10:00 | Visual Brand Creative | Dimas M. | Weekly Update | Tidak Ada | - | - | dimas48@example-fsj.com
2026-07-03 11:00 | Program Management Officer (PMO) | Wulan R. | Weekly Update | Tidak Ada | - | - | wulan64@example-fsj.com
2026-07-05 12:00 | Program Management Officer (PMO) | Putri R. | Monthly Update | - | - | - | putri68@example-fsj.com
2026-07-05 16:00 | Administration & Performance Reporting | Arka H. | Ad Hoc Document Submission | - | - | - | arka37@example-fsj.com
2026-07-06 12:00 | Administration & Performance Reporting | Ilham A. | Ad Hoc Document Submission | - | - | - | ilham98@example-fsj.com
2026-07-07 12:00 | Digital Marketing | Meli W. | Monthly Update | - | - | - | meli39@example-fsj.com
2026-07-08 10:00 | Product & Website UI/UX (Website) | Gilang W. | Event / Program Execution | - | - | - | gilang29@example-fsj.com
2026-07-09 16:00 | Human Resource | Fajar K. | Monthly Update | - | - | - | fajar59@example-fsj.com
2026-07-10 15:00 | PR & Project Execution | Intan S. | Event / Program Execution | - | - | - | intan95@example-fsj.com
2026-07-11 15:00 | Administration & Performance Reporting | Dimas R. | Ad Hoc Document Submission | - | - | - | dimas12@example-fsj.com
2026-07-13 10:00 | Visual Brand Creative | Wulan S. | Weekly Update | Tidak Ada | - | - | wulan75@example-fsj.com
2026-07-13 10:00 | Product & Website UI/UX (Product) | Dimas K. | Weekly Update | Ada | Budget & Finance | Critical | dimas86@example-fsj.com
2026-07-13 15:00 | PR & Project Execution | Meli K. | Weekly Update | Tidak Ada | - | - | meli52@example-fsj.com
2026-07-14 09:00 | Administration & Performance Reporting | Rafi K. | Weekly Update | Tidak Ada | - | - | rafi28@example-fsj.com
2026-07-14 17:00 | Human Resource | Arka S. | Weekly Update | Tidak Ada | - | - | arka35@example-fsj.com
2026-07-15 13:00 | Digital Marketing | Aldo K. | Weekly Update | Ada | Procurement & Vendor | Critical | aldo52@example-fsj.com
2026-07-15 16:00 | Product & Website UI/UX (Website) | Gilang W. | Weekly Update | Tidak Ada | - | - | gilang45@example-fsj.com
2026-07-16 11:00 | Program Management Officer (PMO) | Gilang R. | Weekly Update | Tidak Ada | - | - | gilang66@example-fsj.com
2026-07-16 13:00 | Product & Website UI/UX (Website) | Intan P. | Monthly Update | - | - | - | intan69@example-fsj.com
2026-07-16 17:00 | PR & Project Execution | Rafi P. | Monthly Update | - | - | - | rafi40@example-fsj.com
2026-07-17 14:00 | Sustainability (ESG) | Bima R. | Weekly Update | Tidak Ada | - | - | bima95@example-fsj.com
2026-07-18 11:00 | Product & Website UI/UX (Website) | Rafi M. | Ad Hoc Document Submission | - | - | - | rafi62@example-fsj.com
2026-07-18 15:00 | Administration & Performance Reporting | Putri W. | Quick Link & Asset Submission | - | - | - | putri53@example-fsj.com
2026-07-19 15:00 | Product & Website UI/UX (Product) | Intan S. | Ad Hoc Document Submission | - | - | - | intan51@example-fsj.com
2026-07-20 14:00 | Program Management Officer (PMO) | Dian M. | Quick Link & Asset Submission | - | - | - | dian18@example-fsj.com
2026-07-22 17:00 | Visual Brand Creative | Kayla R. | Ad Hoc Document Submission | - | - | - | kayla38@example-fsj.com
2026-07-24 09:00 | Administration & Performance Reporting | Zahra M. | Quick Link & Asset Submission | - | - | - | zahra40@example-fsj.com
2026-07-25 09:00 | Program Management Officer (PMO) | Gilang R. | Ad Hoc Document Submission | - | - | - | gilang83@example-fsj.com
2026-07-25 17:00 | Human Resource | Arka K. | Event / Program Execution | - | - | - | arka38@example-fsj.com
2026-07-28 09:00 | Program Management Officer (PMO) | Wulan W. | Weekly Update | Tidak Ada | - | - | wulan20@example-fsj.com
2026-07-28 13:00 | Product & Website UI/UX (Product) | Bima A. | Weekly Update | Tidak Ada | - | - | bima48@example-fsj.com
2026-07-28 15:00 | Visual Brand Creative | Nadia K. | Weekly Update | Ada | Human Resource / SDM | High | nadia83@example-fsj.com
2026-07-28 17:00 | PR & Project Execution | Dimas P. | Quick Link & Asset Submission | - | - | - | dimas38@example-fsj.com
2026-07-30 09:00 | Human Resource | Ilham A. | Weekly Update | Tidak Ada | - | - | ilham12@example-fsj.com
2026-07-30 14:00 | Sustainability (ESG) | Kayla S. | Weekly Update | Tidak Ada | - | - | kayla69@example-fsj.com
2026-07-30 16:00 | PR & Project Execution | Dian M. | Weekly Update | Tidak Ada | - | - | dian13@example-fsj.com
2026-07-30 16:00 | PR & Project Execution | Nadia P. | Quick Link & Asset Submission | - | - | - | nadia68@example-fsj.com
2026-07-31 10:00 | Product & Website UI/UX (Website) | Meli A. | Weekly Update | Tidak Ada | - | - | meli23@example-fsj.com
2026-07-31 11:00 | Administration & Performance Reporting | Aldo S. | Weekly Update | Tidak Ada | - | - | aldo24@example-fsj.com
2026-07-31 11:00 | Product & Website UI/UX (Product) | Putri A. | Quick Link & Asset Submission | - | - | - | putri20@example-fsj.com
2026-07-31 12:00 | Human Resource | Zahra W. | Event / Program Execution | - | - | - | zahra30@example-fsj.com
2026-07-31 16:00 | Digital Marketing | Aldo R. | Weekly Update | Tidak Ada | - | - | aldo29@example-fsj.com
2026-08-02 17:00 | Program Management Officer (PMO) | Rafi K. | Ad Hoc Document Submission | - | - | - | rafi17@example-fsj.com
2026-08-03 10:00 | Visual Brand Creative | Aldo S. | Monthly Update | - | - | - | aldo59@example-fsj.com
2026-08-03 14:00 | Product & Website UI/UX (Website) | Wulan P. | Quick Link & Asset Submission | - | - | - | wulan64@example-fsj.com
2026-08-03 15:00 | PR & Project Execution | Nadia W. | Ad Hoc Document Submission | - | - | - | nadia39@example-fsj.com
2026-08-04 10:00 | Program Management Officer (PMO) | Salsa W. | Event / Program Execution | - | - | - | salsa69@example-fsj.com
2026-08-05 10:00 | Human Resource | Dimas P. | Ad Hoc Document Submission | - | - | - | dimas96@example-fsj.com
2026-08-07 17:00 | Product & Website UI/UX (Website) | Zahra A. | Quick Link & Asset Submission | - | - | - | zahra59@example-fsj.com
2026-08-08 09:00 | PR & Project Execution | Reza K. | Monthly Update | - | - | - | reza66@example-fsj.com
2026-08-08 09:00 | Human Resource | Nadia W. | Monthly Update | - | - | - | nadia77@example-fsj.com
2026-08-08 09:00 | Product & Website UI/UX (Website) | Meli K. | Quick Link & Asset Submission | - | - | - | meli28@example-fsj.com
2026-08-08 15:00 | Digital Marketing | Reza P. | Monthly Update | - | - | - | reza96@example-fsj.com
2026-08-10 11:00 | Product & Website UI/UX (Website) | Nadia R. | Weekly Update | Ada | Procurement & Vendor | Low | nadia49@example-fsj.com
2026-08-10 13:00 | Visual Brand Creative | Putri K. | Weekly Update | Tidak Ada | - | - | putri55@example-fsj.com
2026-08-11 13:00 | Administration & Performance Reporting | Rafi A. | Weekly Update | Tidak Ada | - | - | rafi66@example-fsj.com
2026-08-11 14:00 | Visual Brand Creative | Kayla A. | Ad Hoc Document Submission | - | - | - | kayla68@example-fsj.com
2026-08-12 10:00 | Digital Marketing | Nadia S. | Ad Hoc Document Submission | - | - | - | nadia96@example-fsj.com
2026-08-12 11:00 | Product & Website UI/UX (Product) | Rafi R. | Weekly Update | Tidak Ada | - | - | rafi97@example-fsj.com
2026-08-12 14:00 | PR & Project Execution | Wulan R. | Weekly Update | Tidak Ada | - | - | wulan98@example-fsj.com
2026-08-12 15:00 | Visual Brand Creative | Nadia A. | Ad Hoc Document Submission | - | - | - | nadia77@example-fsj.com
2026-08-12 16:00 | Program Management Officer (PMO) | Wulan R. | Weekly Update | Tidak Ada | - | - | wulan71@example-fsj.com
2026-08-12 16:00 | Human Resource | Putri R. | Event / Program Execution | - | - | - | putri45@example-fsj.com
2026-08-12 17:00 | Human Resource | Gilang R. | Weekly Update | Tidak Ada | - | - | gilang78@example-fsj.com
2026-08-13 12:00 | Human Resource | Intan P. | Event / Program Execution | - | - | - | intan74@example-fsj.com
2026-08-13 14:00 | Digital Marketing | Putri S. | Weekly Update | Tidak Ada | - | - | putri41@example-fsj.com
2026-08-13 14:00 | Product & Website UI/UX (Website) | Putri W. | Monthly Update | - | - | - | putri63@example-fsj.com
2026-08-13 16:00 | Sustainability (ESG) | Putri A. | Weekly Update | Ada | Procurement & Vendor | Critical | putri52@example-fsj.com
2026-08-14 10:00 | Sustainability (ESG) | Citra A. | Monthly Update | - | - | - | citra16@example-fsj.com
2026-08-16 13:00 | Administration & Performance Reporting | Putri A. | Monthly Update | - | - | - | putri17@example-fsj.com
2026-08-17 11:00 | Program Management Officer (PMO) | Zahra P. | Event / Program Execution | - | - | - | zahra46@example-fsj.com
2026-08-18 14:00 | Sustainability (ESG) | Meli W. | Quick Link & Asset Submission | - | - | - | meli33@example-fsj.com
2026-08-19 09:00 | Program Management Officer (PMO) | Wulan S. | Monthly Update | - | - | - | wulan26@example-fsj.com
2026-08-19 11:00 | Product & Website UI/UX (Product) | Fajar H. | Event / Program Execution | - | - | - | fajar39@example-fsj.com
2026-08-20 14:00 | Visual Brand Creative | Nadia M. | Event / Program Execution | - | - | - | nadia20@example-fsj.com
2026-08-20 17:00 | Product & Website UI/UX (Product) | Intan W. | Monthly Update | - | - | - | intan86@example-fsj.com
2026-08-24 10:00 | Human Resource | Nadia A. | Quick Link & Asset Submission | - | - | - | nadia55@example-fsj.com

## Data_Weekly
Timestamp | Divisi | PIC | Periode | Output Utama Week Ini | Status Pekerjaan | Progress (%) | Task Selesai Week Ini | Target Task Depan | Ada Isu | Kategori Isu | Prioritas Isu | Butuh Support Divisi Lain | Divisi yang Dibutuhkan
2026-06-01 09:00 | Digital Marketing | Wulan K. | Week 1 | Riset kompetitor & benchmarking | 🟢 On Track | 25% | 3 | 5 | Ada | Budget & Finance | Low | Tidak | Digital Marketing
2026-06-01 10:00 | PR & Project Execution | Kayla P. | Week 3 | Merilis konten campaign mingguan | 🟢 On Track | 100% | 10 | 3 | Tidak Ada | - | - | Tidak | -
2026-06-01 17:00 | Sustainability (ESG) | Fajar M. | Week 1 | Menyelesaikan draft SOP divisi | 🟡 Need Attention | 75% | 3 | 5 | Tidak Ada | - | - | Tidak | -
2026-06-02 17:00 | Visual Brand Creative | Dimas K. | Week 3 | Menyelesaikan draft SOP divisi | 🟡 Need Attention | 100% | 7 | 6 | Tidak Ada | - | - | Ya | -
2026-06-03 12:00 | Administration & Performance Reporting | Arka W. | Week 4 | Menyusun proposal kerja sama | 🔴 Delayed | 50% | 5 | 10 | Tidak Ada | - | - | Tidak | -
2026-06-03 16:00 | Program Management Officer (PMO) | Reza S. | Week 2 | Merilis konten campaign mingguan | 🟢 On Track | 50% | 10 | 5 | Tidak Ada | - | - | Ya | -
2026-06-03 17:00 | Human Resource | Aldo M. | Week 1 | Meeting koordinasi lintas divisi | 🟢 On Track | 75% | 8 | 6 | Tidak Ada | - | - | Ya | -
2026-06-04 10:00 | Product & Website UI/UX (Website) | Kayla W. | Week 4 | Merilis konten campaign mingguan | 🟢 On Track | 25% | 12 | 10 | Tidak Ada | - | - | Tidak | -
2026-06-04 15:00 | Product & Website UI/UX (Product) | Reza K. | Week 2 | Update dashboard tracking internal | 🟢 On Track | 25% | 3 | 4 | Tidak Ada | - | - | Tidak | -
2026-06-15 14:00 | Visual Brand Creative | Arka A. | Week 2 | Menyelesaikan draft SOP divisi | 🟡 Need Attention | 25% | 3 | 9 | Ada | IT & Technical | High | Tidak | Product & Website UI/UX (Website)
2026-06-16 12:00 | Product & Website UI/UX (Website) | Fajar K. | Week 1 | Finalisasi laporan bulanan | 🟢 On Track | 25% | 11 | 9 | Tidak Ada | - | - | Tidak | -
2026-06-16 15:00 | Product & Website UI/UX (Product) | Rafi S. | Week 4 | Merilis konten campaign mingguan | ✅ Completed | 75% | 8 | 10 | Tidak Ada | - | - | Tidak | -
2026-06-16 16:00 | PR & Project Execution | Ilham S. | Week 4 | Meeting koordinasi lintas divisi | 🟡 Need Attention | 75% | 8 | 7 | Tidak Ada | - | - | Tidak | -
2026-06-17 10:00 | Digital Marketing | Fajar W. | Week 2 | Menjalankan sesi training internal | 🔴 Delayed | 50% | 4 | 7 | Ada | Legal & Contract | High | Tidak | Product & Website UI/UX (Website)
2026-06-18 10:00 | Sustainability (ESG) | Aldo K. | Week 2 | Menyelesaikan draft SOP divisi | 🟢 On Track | 25% | 5 | 3 | Ada | Legal & Contract | Medium | Tidak | Human Resource
2026-06-18 12:00 | Administration & Performance Reporting | Salsa H. | Week 1 | Menyelesaikan draft SOP divisi | 🟢 On Track | 25% | 5 | 4 | Tidak Ada | - | - | Tidak | -
2026-06-18 16:00 | Human Resource | Rafi P. | Week 1 | Meeting koordinasi lintas divisi | 🟡 Need Attention | 50% | 10 | 9 | Ada | Budget & Finance | High | Ya | PR & Project Execution
2026-06-19 12:00 | Program Management Officer (PMO) | Wulan H. | Week 2 | Update dashboard tracking internal | ✅ Completed | 50% | 3 | 3 | Ada | Procurement & Vendor | Critical | Tidak | Human Resource
2026-06-30 09:00 | Digital Marketing | Zahra P. | Week 1 | Menjalankan sesi training internal | 🟡 Need Attention | 100% | 3 | 5 | Tidak Ada | - | - | Tidak | -
2026-06-30 17:00 | Administration & Performance Reporting | Rafi M. | Week 2 | Riset kompetitor & benchmarking | 🟡 Need Attention | 25% | 6 | 7 | Tidak Ada | - | - | Tidak | -
2026-07-01 09:00 | Human Resource | Dian M. | Week 3 | Menyusun proposal kerja sama | ✅ Completed | 100% | 10 | 2 | Tidak Ada | - | - | Ya | -
2026-07-01 12:00 | Product & Website UI/UX (Product) | Aldo P. | Week 4 | Menyusun proposal kerja sama | 🟡 Need Attention | 50% | 4 | 8 | Tidak Ada | - | - | Ya | -
2026-07-01 13:00 | Sustainability (ESG) | Yoga H. | Week 3 | Menyelesaikan draft SOP divisi | 🔴 Delayed | 25% | 4 | 6 | Tidak Ada | - | - | Ya | -
2026-07-02 12:00 | Product & Website UI/UX (Website) | Wulan S. | Week 1 | Riset kompetitor & benchmarking | 🟢 On Track | 100% | 5 | 5 | Tidak Ada | - | - | Tidak | -
2026-07-02 14:00 | PR & Project Execution | Salsa A. | Week 1 | Menjalankan sesi training internal | 🟡 Need Attention | 75% | 4 | 7 | Tidak Ada | - | - | Tidak | -
2026-07-03 10:00 | Visual Brand Creative | Dimas M. | Week 2 | Finalisasi laporan bulanan | 🟡 Need Attention | 75% | 8 | 4 | Tidak Ada | - | - | Tidak | -
2026-07-03 11:00 | Program Management Officer (PMO) | Wulan R. | Week 3 | Meeting koordinasi lintas divisi | 🔴 Delayed | 100% | 6 | 2 | Tidak Ada | - | - | Ya | -
2026-07-13 10:00 | Visual Brand Creative | Wulan S. | Week 3 | Menyelesaikan draft SOP divisi | 🟢 On Track | 100% | 7 | 7 | Tidak Ada | - | - | Tidak | -
2026-07-13 10:00 | Product & Website UI/UX (Product) | Dimas K. | Week 1 | Meeting koordinasi lintas divisi | 🟢 On Track | 100% | 4 | 9 | Ada | Budget & Finance | Critical | Tidak | Product & Website UI/UX (Website)
2026-07-13 15:00 | PR & Project Execution | Meli K. | Week 4 | Menyelesaikan draft SOP divisi | 🟡 Need Attention | 75% | 8 | 3 | Tidak Ada | - | - | Tidak | -
2026-07-14 09:00 | Administration & Performance Reporting | Rafi K. | Week 1 | Update dashboard tracking internal | ✅ Completed | 50% | 8 | 9 | Tidak Ada | - | - | Tidak | -
2026-07-14 17:00 | Human Resource | Arka S. | Week 3 | Finalisasi laporan bulanan | 🟢 On Track | 50% | 12 | 6 | Tidak Ada | - | - | Tidak | -
2026-07-15 13:00 | Digital Marketing | Aldo K. | Week 3 | Merilis konten campaign mingguan | 🟢 On Track | 75% | 7 | 10 | Ada | Procurement & Vendor | Critical | Tidak | Product & Website UI/UX (Website)
2026-07-15 16:00 | Product & Website UI/UX (Website) | Gilang W. | Week 4 | Menyusun proposal kerja sama | ✅ Completed | 100% | 6 | 5 | Tidak Ada | - | - | Tidak | -
2026-07-16 11:00 | Program Management Officer (PMO) | Gilang R. | Week 1 | Merilis konten campaign mingguan | 🔴 Delayed | 50% | 8 | 7 | Tidak Ada | - | - | Tidak | -
2026-07-17 14:00 | Sustainability (ESG) | Bima R. | Week 4 | Finalisasi laporan bulanan | ✅ Completed | 75% | 10 | 4 | Tidak Ada | - | - | Ya | -
2026-07-28 09:00 | Program Management Officer (PMO) | Wulan W. | Week 4 | Finalisasi laporan bulanan | 🔴 Delayed | 100% | 6 | 8 | Tidak Ada | - | - | Tidak | -
2026-07-28 13:00 | Product & Website UI/UX (Product) | Bima A. | Week 4 | Riset kompetitor & benchmarking | 🟡 Need Attention | 25% | 11 | 5 | Tidak Ada | - | - | Ya | -
2026-07-28 15:00 | Visual Brand Creative | Nadia K. | Week 4 | Riset kompetitor & benchmarking | 🟢 On Track | 50% | 8 | 8 | Ada | Human Resource / SDM | High | Tidak | Digital Marketing
2026-07-30 09:00 | Human Resource | Ilham A. | Week 3 | Meeting koordinasi lintas divisi | 🟢 On Track | 25% | 2 | 5 | Tidak Ada | - | - | Ya | -
2026-07-30 14:00 | Sustainability (ESG) | Kayla S. | Week 2 | Menyelesaikan draft SOP divisi | ✅ Completed | 25% | 3 | 8 | Tidak Ada | - | - | Ya | -
2026-07-30 16:00 | PR & Project Execution | Dian M. | Week 4 | Riset kompetitor & benchmarking | 🟡 Need Attention | 100% | 5 | 6 | Tidak Ada | - | - | Tidak | -
2026-07-31 10:00 | Product & Website UI/UX (Website) | Meli A. | Week 4 | Finalisasi laporan bulanan | 🟢 On Track | 75% | 2 | 8 | Tidak Ada | - | - | Tidak | -
2026-07-31 11:00 | Administration & Performance Reporting | Aldo S. | Week 1 | Meeting koordinasi lintas divisi | ✅ Completed | 75% | 7 | 4 | Tidak Ada | - | - | Tidak | -
2026-07-31 16:00 | Digital Marketing | Aldo R. | Week 3 | Meeting koordinasi lintas divisi | 🔴 Delayed | 75% | 7 | 10 | Tidak Ada | - | - | Ya | -
2026-08-10 11:00 | Product & Website UI/UX (Website) | Nadia R. | Week 4 | Meeting koordinasi lintas divisi | ✅ Completed | 100% | 9 | 6 | Ada | Procurement & Vendor | Low | Tidak | Administration & Performance Reporting
2026-08-10 13:00 | Visual Brand Creative | Putri K. | Week 4 | Finalisasi laporan bulanan | 🟢 On Track | 100% | 7 | 4 | Tidak Ada | - | - | Tidak | -
2026-08-11 13:00 | Administration & Performance Reporting | Rafi A. | Week 2 | Update dashboard tracking internal | 🟢 On Track | 25% | 11 | 6 | Tidak Ada | - | - | Tidak | -
2026-08-12 11:00 | Product & Website UI/UX (Product) | Rafi R. | Week 4 | Menjalankan sesi training internal | 🟢 On Track | 100% | 9 | 3 | Tidak Ada | - | - | Tidak | -
2026-08-12 14:00 | PR & Project Execution | Wulan R. | Week 2 | Menjalankan sesi training internal | 🟡 Need Attention | 100% | 9 | 10 | Tidak Ada | - | - | Tidak | -
2026-08-12 16:00 | Program Management Officer (PMO) | Wulan R. | Week 1 | Meeting koordinasi lintas divisi | 🔴 Delayed | 25% | 10 | 4 | Tidak Ada | - | - | Ya | -
2026-08-12 17:00 | Human Resource | Gilang R. | Week 2 | Merilis konten campaign mingguan | 🟡 Need Attention | 75% | 4 | 6 | Tidak Ada | - | - | Ya | -
2026-08-13 14:00 | Digital Marketing | Putri S. | Week 3 | Update dashboard tracking internal | ✅ Completed | 100% | 11 | 6 | Tidak Ada | - | - | Tidak | -
2026-08-13 16:00 | Sustainability (ESG) | Putri A. | Week 2 | Merilis konten campaign mingguan | 🔴 Delayed | 100% | 10 | 10 | Ada | Procurement & Vendor | Critical | Tidak | Product & Website UI/UX (Website)

## Data_Monthly
Timestamp | Divisi | Bulan | Pencapaian Terbesar | Lesson Learned
2026-06-04 11:00 | Program Management Officer (PMO) | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-06-05 16:00 | Product & Website UI/UX (Product) | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-06-08 09:00 | Sustainability (ESG) | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-06-09 15:00 | Product & Website UI/UX (Website) | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-06-13 17:00 | Human Resource | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-06-15 10:00 | Visual Brand Creative | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-06-15 16:00 | Administration & Performance Reporting | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-06-19 09:00 | Digital Marketing | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-06-20 13:00 | PR & Project Execution | Juni | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-01 11:00 | Visual Brand Creative | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-02 13:00 | Sustainability (ESG) | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-02 14:00 | Product & Website UI/UX (Product) | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-02 16:00 | Administration & Performance Reporting | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-05 12:00 | Program Management Officer (PMO) | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-07 12:00 | Digital Marketing | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-09 16:00 | Human Resource | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-16 13:00 | Product & Website UI/UX (Website) | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-07-16 17:00 | PR & Project Execution | Juli | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-03 10:00 | Visual Brand Creative | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-08 09:00 | PR & Project Execution | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-08 09:00 | Human Resource | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-08 15:00 | Digital Marketing | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-13 14:00 | Product & Website UI/UX (Website) | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-14 10:00 | Sustainability (ESG) | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-16 13:00 | Administration & Performance Reporting | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-19 09:00 | Program Management Officer (PMO) | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.
2026-08-20 17:00 | Product & Website UI/UX (Product) | Agustus | Pencapaian signifikan pada inisiatif utama bulan ini, target tercapai sesuai rencana. | Koordinasi lebih awal dengan tim lain mempercepat proses eksekusi.

## Data_Divisi_DigitalMarketing
Timestamp | Sub-Divisi | Nama Campaign | Status Campaign | Target Tanggal | Total Konten Terpublikasi | Total Reach Konten | Average Engagement Rate | Total Post LinkedIn | Total Impressions LinkedIn | Total Broadcast/Leads CRM | Average Open/Click Rate CRM | Peak Viewers Live Stream | Evaluasi Performance | Next Action Plan
2026-06-19 09:00 | CRM Specialist | Live IG Sharing Session 1 | Planning | 2026-06-28 09:00 | 15 | 2043 | 4.66 | 11 | 4349 | 94 | 11.1 | 197 | Engagement meningkat dibanding bulan lalu, konten reels paling efektif. | Fokus konten video pendek & kolaborasi micro-influencer bulan depan.
2026-07-07 12:00 | Strategic & Engagement | Branding Feeds IG 2 | On Hold | 2026-07-23 12:00 | 40 | 2606 | 2.82 | 11 | 3219 | 45 | 40.6 | 275 | Engagement meningkat dibanding bulan lalu, konten reels paling efektif. | Fokus konten video pendek & kolaborasi micro-influencer bulan depan.
2026-08-08 15:00 | CV & LinkedIn | Branding Feeds IG 3 | Planning | 2026-08-18 15:00 | 30 | 9606 | 7.91 | 6 | 3844 | 49 | 14.9 | 69 | Engagement meningkat dibanding bulan lalu, konten reels paling efektif. | Fokus konten video pendek & kolaborasi micro-influencer bulan depan.

## Data_Divisi_VBC
Timestamp | Sub-Divisi | Nama Program/Inisiatif | Objective | Sasaran/Target Audiens | Target Tanggal Pelaksanaan | Status Progress Project | Tim Penanggung Jawab | Total Asset Desain Sosmed | Total Design Event/Collab | Status/Evaluasi Project
2026-06-15 10:00 | Visual Creative | Redesign Template Laporan | Meningkatkan konsistensi visual brand di seluruh kanal komunikasi. | Internal FSJ | 2026-06-24 10:00 | In Progress | Dimas P., Ilham K. | 14 | 2 | Proses desain lancar, revisi minor dari tim terkait.
2026-07-01 11:00 | Visual Creative | Redesign Template Laporan | Meningkatkan konsistensi visual brand di seluruh kanal komunikasi. | Internal FSJ | 2026-07-19 11:00 | Completed | Wulan M., Gilang W. | 30 | 12 | Proses desain lancar, revisi minor dari tim terkait.
2026-08-03 10:00 | Visual Executor | Branding Kit Launch | Meningkatkan konsistensi visual brand di seluruh kanal komunikasi. | Internal FSJ | 2026-08-20 10:00 | Completed | Reza W., Meli S. | 49 | 8 | Proses desain lancar, revisi minor dari tim terkait.

## Data_Divisi_PR
Timestamp | Sub-Divisi/Role | Nama Inisiatif | Scope PR/Project | Sasaran/Target Impact | Target Tanggal | Status Progress | Tim Penanggung Jawab | Total Partner/Media Contacted | Total Deals Completed | Total Event Execution | Detail Progress & Evaluasi | Next Action Plan
2026-06-20 13:00 | Project Execution | Partnership Media Kampus | Media Relation | Mitra/Sponsor | 2026-07-02 13:00 | Outreach / Pitching | Kayla R., Zahra H. | 18 | 6 | 5 | Respon partner cukup positif, proses negosiasi berjalan sesuai timeline. | Follow up lanjutan dengan 2 calon partner baru bulan depan.
2026-07-16 17:00 | Public Relations | Kolaborasi Sponsor Event | Media Relation | Mitra/Sponsor | 2026-07-28 17:00 | Negotiation / Drafting MoU | Aldo P., Dimas P. | 27 | 5 | 1 | Respon partner cukup positif, proses negosiasi berjalan sesuai timeline. | Follow up lanjutan dengan 2 calon partner baru bulan depan.
2026-08-08 09:00 | Project Execution | Partnership Media Kampus | Media Relation | Mitra/Sponsor | 2026-08-25 09:00 | On Hold | Aldo M., Bima M. | 13 | 4 | 1 | Respon partner cukup positif, proses negosiasi berjalan sesuai timeline. | Follow up lanjutan dengan 2 calon partner baru bulan depan.

## Data_Divisi_ESG
Timestamp | Sub-Focus ESG | Nama Program/Inisiatif | Focus Area ESG | Target Tanggal | Status Project | Sasaran/Target Impact | Detail Progress & Capaian | Tim Penanggung Jawab | Total Respondent/Field Data | Total Research Paper/Report | Total Partnership Contacted | Evaluasi Project & Obstacles | Next Action Plan
2026-06-08 09:00 | Business Development | Riset Dampak Sosial Program | Environmental (E) | 2026-06-26 09:00 | Completed | Komunitas Lokal | Progres pengumpulan data sesuai target, analisis awal menunjukkan tren positif. | Zahra H., Wulan S. | 43 | 3 | 7 | Beberapa kendala akses lokasi survei di minggu pertama. | Perluas cakupan survei ke 2 lokasi tambahan.
2026-07-02 13:00 | Field & Survey | Survei Kesadaran Lingkungan | Environmental (E) | 2026-07-09 13:00 | Planning / Desk Research | Komunitas Lokal | Progres pengumpulan data sesuai target, analisis awal menunjukkan tren positif. | Aldo W., Meli S. | 117 | 1 | 9 | Beberapa kendala akses lokasi survei di minggu pertama. | Perluas cakupan survei ke 2 lokasi tambahan.
2026-08-14 10:00 | Field & Survey | Partnership CSR Lokal | Environmental (E) | 2026-08-27 10:00 | In Progress | Komunitas Lokal | Progres pengumpulan data sesuai target, analisis awal menunjukkan tren positif. | Aldo S., Meli K. | 75 | 1 | 7 | Beberapa kendala akses lokasi survei di minggu pertama. | Perluas cakupan survei ke 2 lokasi tambahan.

## Data_Divisi_PMO
Timestamp | Sub-Divisi/Program PMO | Nama Program/Event/Project | Jenis Activity/Focus Milestone | Sasaran/Target Impact | Target Tanggal | Status Execution | Tim Penanggung Jawab | Total Peserta/Registrant | Total Project/Task On-Time | Overall Timeline Health (%) | Detail Progress & Risk Eval | Next Action & Mitigasi
2026-06-04 11:00 | Project Tracker & Reporting | Execution Webinar Step Talk Vol.1 | Event Execution | Peserta Eksternal | 2026-06-22 11:00 | Completed | Fajar W., Ilham A. | 62 | 13 | 67 | Timeline berjalan sesuai rencana, minor delay pada 1 milestone. | Perketat monitoring milestone minggu ke-2 bulan depan.
2026-07-05 12:00 | Big Project FSJ | Timeline Health Check Batch Vol.2 | Event Execution | Peserta Eksternal | 2026-07-16 12:00 | Completed | Dian H., Fajar S. | 105 | 12 | 100 | Timeline berjalan sesuai rencana, minor delay pada 1 milestone. | Perketat monitoring milestone minggu ke-2 bulan depan.
2026-08-19 09:00 | Step Up College | Execution Webinar Step Talk Vol.3 | Event Execution | Peserta Eksternal | 2026-09-08 09:00 | Completed | Wulan S., Bima A. | 131 | 10 | 97 | Timeline berjalan sesuai rencana, minor delay pada 1 milestone. | Perketat monitoring milestone minggu ke-2 bulan depan.

## Data_Divisi_HR
Timestamp | Sub-Divisi/Focus HR | Nama Program/Inisiatif | Deskripsi & Objective | Sasaran/Target Audiens | Status Progress Program | Tim Penanggung Jawab | Target Tanggal Pelaksanaan | Total Pelamar/Evaluated | Total Partisipan Culture | Total Peserta Training | Evaluasi Program | Tindak Lanjut
2026-06-13 17:00 | People Development | Performance Review Q | Meningkatkan engagement dan skill anggota tim. | Intern FSJ Batch | Planning | Citra M., Gilang H. | 2026-06-17 17:00 | 16 | 32 | 45 | Partisipasi cukup tinggi, feedback peserta positif. | Jadwalkan sesi lanjutan dengan topik lebih spesifik.
2026-07-09 16:00 | People Development | Gathering Semester | Meningkatkan engagement dan skill anggota tim. | Intern FSJ Batch | Completed | Bima K., Kayla M. | 2026-07-27 16:00 | 10 | 57 | 35 | Partisipasi cukup tinggi, feedback peserta positif. | Jadwalkan sesi lanjutan dengan topik lebih spesifik.
2026-08-08 09:00 | People Development | Internal Training Emotional Regulation | Meningkatkan engagement dan skill anggota tim. | Intern FSJ Batch | On Hold | Salsa H., Putri M. | 2026-08-14 09:00 | 26 | 29 | 49 | Partisipasi cukup tinggi, feedback peserta positif. | Jadwalkan sesi lanjutan dengan topik lebih spesifik.

## Data_Divisi_ACR
Timestamp | Sub-Divisi/Focus ACR | Nama Program/Inisiatif | Objective & Operational Goals | Target Tanggal/Deadline | Status Overall Project | Progress Update | Tim Penanggung Jawab | Metrik Hasil Reporting | Metrik Hasil Dashboard | Gap/Metrik Masalah (%) | Deskripsi Root Cause | Operational Goals & Target
2026-06-15 16:00 | Dashboard | Calendar of Event (CoE) | Meningkatkan visibilitas performa pelaporan seluruh divisi. | 2026-06-25 16:00 | In Progress | Template selesai, pengisian oleh divisi lain berjalan bertahap. | Yoga R., Ilham A. | 4 | 4 | 28.68 | Beberapa divisi masih terlambat submit laporan mingguan. | Reminder otomatis & sesi sosialisasi ulang ke seluruh divisi.
2026-07-02 16:00 | Reporting | Rekap KPI Bulanan | Meningkatkan visibilitas performa pelaporan seluruh divisi. | 2026-07-16 16:00 | Planning | Template selesai, pengisian oleh divisi lain berjalan bertahap. | Aldo K., Gilang R. | 13 | 6 | 5.99 | Beberapa divisi masih terlambat submit laporan mingguan. | Reminder otomatis & sesi sosialisasi ulang ke seluruh divisi.
2026-08-16 13:00 | Dashboard | Calendar of Event (CoE) | Meningkatkan visibilitas performa pelaporan seluruh divisi. | 2026-09-03 13:00 | Planning | Template selesai, pengisian oleh divisi lain berjalan bertahap. | Kayla W., Bima H. | 8 | 5 | 8.71 | Beberapa divisi masih terlambat submit laporan mingguan. | Reminder otomatis & sesi sosialisasi ulang ke seluruh divisi.

## Data_Divisi_Product
Timestamp | Sub-Program Product | Nama Produk/Inisiatif | Deskripsi & Objective | Sasaran/Target Audiens | Target Tanggal Release | Status Progress Project | Tim Penanggung Jawab | Total Sesi/Member Terlayani | Total Active Users | Average Satisfaction Score | Evaluasi Operational | Next Action Plan
2026-06-05 16:00 | Product (CV Review) | FSJ Essentials Modul Baru | Meningkatkan kualitas layanan & kepuasan pengguna produk. | Mahasiswa | 2026-06-23 16:00 | Completed / Released | Arka K., Putri S. | 75 | 241 | 4.8 | Beberapa kendala teknis minor pada proses onboarding. | Perbaikan alur onboarding & tambah sesi FAQ.
2026-07-02 14:00 | Product (1o1 Review) | 1on1 Mentoring Program | Meningkatkan kualitas layanan & kepuasan pengguna produk. | Mahasiswa | 2026-07-15 14:00 | Completed / Released | Dimas S., Citra S. | 74 | 283 | 3.9 | Beberapa kendala teknis minor pada proses onboarding. | Perbaikan alur onboarding & tambah sesi FAQ.
2026-08-20 17:00 | Product (E-Learning) | CV Review Batch | Meningkatkan kualitas layanan & kepuasan pengguna produk. | Mahasiswa | 2026-09-08 17:00 | Planning / Riset | Fajar H., Zahra W. | 80 | 234 | 4.8 | Beberapa kendala teknis minor pada proses onboarding. | Perbaikan alur onboarding & tambah sesi FAQ.

## Data_Divisi_Website
Timestamp | Sub-Divisi/Tech Focus | Nama Fitur/Module | Deskripsi Development | Target Tanggal Deploy | Status Development | Tim Penanggung Jawab | Total Screens/Wireframe | Total Sprints/Issues | Total Visitors/Page Views | Technical Obstacles
2026-06-09 15:00 | Website (Coasterra) | Integrasi Payment Gateway | Meningkatkan performa & pengalaman pengguna website. | 2026-06-21 15:00 | Testing | Fajar H., Nadia H. | 20 | 14 | 4951 | Load time sedikit meningkat di halaman utama, perlu optimasi gambar.
2026-07-16 13:00 | UI/UX | Optimasi Loading Speed | Meningkatkan performa & pengalaman pengguna website. | 2026-07-21 13:00 | Wireframing | Nadia K., Kayla M. | 11 | 10 | 1512 | Load time sedikit meningkat di halaman utama, perlu optimasi gambar.
2026-08-13 14:00 | Website (Back End) | Fix Bug API Auth | Meningkatkan performa & pengalaman pengguna website. | 2026-08-19 14:00 | Live Deployed | Intan W., Intan R. | 5 | 3 | 1199 | Load time sedikit meningkat di halaman utama, perlu optimasi gambar.

## Data_AdHoc
Timestamp | Divisi | PIC | Jenis Dokumen | Judul Dokumen | Keterangan
2026-06-04 11:00 | Program Management Officer (PMO) | Fajar M. | Legal Document | Notulensi Meeting Vendor #5 | Dokumen sudah direview coach terkait.
2026-06-22 10:00 | Product & Website UI/UX (Website) | Bima K. | Legal Document | MoU Draft Partner #18 | Dokumen sudah direview coach terkait.
2026-06-22 16:00 | Human Resource | Salsa W. | Meeting Minutes (MoM) | SOP Onboarding Intern #16 | Dokumen sudah direview coach terkait.
2026-06-27 13:00 | Sustainability (ESG) | Nadia R. | Legal Document | MoU Draft Partner #12 | Dokumen sudah direview coach terkait.
2026-06-28 11:00 | Product & Website UI/UX (Product) | Aldo P. | Legal Document | Materi Sharing Session Internal #3 | Dokumen sudah direview coach terkait.
2026-07-05 16:00 | Administration & Performance Reporting | Arka H. | Report (Weekly/Monthly) | MoU Draft Partner #9 | Dokumen sudah direview coach terkait.
2026-07-06 12:00 | Administration & Performance Reporting | Ilham A. | Knowledge Sharing | Kontrak Kerja Sama Sponsor #4 | Dokumen sudah direview coach terkait.
2026-07-11 15:00 | Administration & Performance Reporting | Dimas R. | Meeting Minutes (MoM) | Report Evaluasi Triwulan #15 | Dokumen sudah direview coach terkait.
2026-07-18 11:00 | Product & Website UI/UX (Website) | Rafi M. | Contract / Agreement | Notulensi Meeting Vendor #1 | Dokumen sudah direview coach terkait.
2026-07-19 15:00 | Product & Website UI/UX (Product) | Intan S. | Legal Document | MoU Draft Partner #7 | Dokumen sudah direview coach terkait.
2026-07-22 17:00 | Visual Brand Creative | Kayla R. | Contract / Agreement | MoU Draft Partner #17 | Dokumen sudah direview coach terkait.
2026-07-25 09:00 | Program Management Officer (PMO) | Gilang R. | Legal Document | Notulensi Meeting Vendor #2 | Dokumen sudah direview coach terkait.
2026-08-02 17:00 | Program Management Officer (PMO) | Rafi K. | Report (Weekly/Monthly) | Materi Sharing Session Internal #11 | Dokumen sudah direview coach terkait.
2026-08-03 15:00 | PR & Project Execution | Nadia W. | Knowledge Sharing | Kontrak Kerja Sama Sponsor #13 | Dokumen sudah direview coach terkait.
2026-08-05 10:00 | Human Resource | Dimas P. | Legal Document | Kontrak Kerja Sama Sponsor #10 | Dokumen sudah direview coach terkait.
2026-08-11 14:00 | Visual Brand Creative | Kayla A. | Report (Weekly/Monthly) | Notulensi Meeting Vendor #14 | Dokumen sudah direview coach terkait.
2026-08-12 10:00 | Digital Marketing | Nadia S. | Knowledge Sharing | Notulensi Meeting Vendor #8 | Dokumen sudah direview coach terkait.
2026-08-12 15:00 | Visual Brand Creative | Nadia A. | Meeting Minutes (MoM) | Kontrak Kerja Sama Sponsor #6 | Dokumen sudah direview coach terkait.

## Data_Event
Timestamp | Divisi | Nama Program/Event | Status/Kategori Event | Tanggal Pelaksanaan | Target Pendaftar | Realisasi Peserta Hadir | Jumlah Asal Universitas | Jumlah Asal Daerah
2026-06-19 12:00 | Visual Brand Creative | Bootcamp Data Analyst Mini Vol.1 | Internal | 2026-06-29 12:00 | 48 | 42 | 7 | 14
2026-07-02 16:00 | Product & Website UI/UX (Product) | Sharing Session Alumni Vol.5 | Eksternal | 2026-07-08 16:00 | 97 | 74 | 12 | 8
2026-07-08 10:00 | Product & Website UI/UX (Website) | Webinar Karir Digital Vol.9 | Collaboration | 2026-07-14 10:00 | 128 | 104 | 22 | 4
2026-07-10 15:00 | PR & Project Execution | Talkshow Mental Health at Work Vol.7 | Collaboration | 2026-07-17 15:00 | 106 | 111 | 23 | 14
2026-07-25 17:00 | Human Resource | Talkshow Mental Health at Work Vol.8 | Internal | 2026-07-29 17:00 | 32 | 19 | 13 | 14
2026-07-31 12:00 | Human Resource | Career Fair Kampus Mitra Vol.11 | Eksternal | 2026-08-05 12:00 | 116 | 90 | 15 | 10
2026-08-04 10:00 | Program Management Officer (PMO) | Webinar Karir Digital Vol.3 | Internal | 2026-08-10 10:00 | 89 | 71 | 12 | 3
2026-08-12 16:00 | Human Resource | Kompetisi Case Study Batch Vol.2 | Internal | 2026-08-20 16:00 | 140 | 110 | 5 | 9
2026-08-13 12:00 | Human Resource | Sharing Session Alumni Vol.4 | Internal | 2026-08-21 12:00 | 107 | 87 | 6 | 14
2026-08-17 11:00 | Program Management Officer (PMO) | Kompetisi Case Study Batch Vol.12 | Collaboration | 2026-08-19 11:00 | 36 | 16 | 25 | 15
2026-08-19 11:00 | Product & Website UI/UX (Product) | Kompetisi Case Study Batch Vol.10 | Collaboration | 2026-08-23 11:00 | 35 | 19 | 17 | 11
2026-08-20 14:00 | Visual Brand Creative | Open House FSJ Vol.6 | Eksternal | 2026-08-25 14:00 | 72 | 76 | 24 | 11

## Data_Link
Timestamp | Divisi | Jalur | Judul/Nama Link | URL | Sumber
2026-06-04 11:00 | Program Management Officer (PMO) | Ad Hoc Document Submission | 2026-06-04_ProgramManageme_AdHoc_Legal.pdf | https://drive.google.com/file/d/DUMMY-250210/view | File Upload
2026-06-05 12:00 | Program Management Officer (PMO) | Quick Link & Asset Submission | Wireframe Figma Landing Page Batch 3 | https://www.figma.com/file/DUMMY-230521 | Quick Link
2026-06-06 12:00 | Digital Marketing | Quick Link & Asset Submission | SOP Digital Onboarding Update | https://www.figma.com/file/DUMMY-365618 | Quick Link
2026-06-07 12:00 | Administration & Performance Reporting | Quick Link & Asset Submission | Dashboard Notion Tracker Divisi Update | https://www.figma.com/file/DUMMY-725726 | Quick Link
2026-06-08 09:00 | Sustainability (ESG) | Monthly Update | 2026-06-08_Sustainability(_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-436653/view | File Upload
2026-06-09 15:00 | Product & Website UI/UX (Website) | Monthly Update | 2026-06-09_Product&Website_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-437408/view | File Upload
2026-06-13 17:00 | Human Resource | Monthly Update | 2026-06-13_HumanResource_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-402020/view | File Upload
2026-06-15 10:00 | Visual Brand Creative | Monthly Update | 2026-06-15_VisualBrandCrea_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-422554/view | File Upload
2026-06-19 12:00 | Visual Brand Creative | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-618119/edit | Event Asset
2026-06-19 12:00 | Visual Brand Creative | Event / Program Execution | Dokumentasi_Career Fair Kampus Mitra_20260619 | https://drive.google.com/drive/folders/DUMMY-891093 | Event Asset
2026-06-20 13:00 | PR & Project Execution | Monthly Update | 2026-06-20_PR&ProjectExecu_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-195763/view | File Upload
2026-06-20 17:00 | Product & Website UI/UX (Website) | Quick Link & Asset Submission | Spreadsheet Tracking Anggota Batch 3 | https://www.figma.com/file/DUMMY-227767 | Quick Link
2026-06-22 10:00 | Product & Website UI/UX (Website) | Ad Hoc Document Submission | 2026-06-22_Product&Website_AdHoc_Legal.pdf | https://drive.google.com/file/d/DUMMY-954628/view | File Upload
2026-06-22 16:00 | Human Resource | Ad Hoc Document Submission | 2026-06-22_HumanResource_AdHoc_Meeting.pdf | https://drive.google.com/file/d/DUMMY-717476/view | File Upload
2026-06-27 13:00 | Sustainability (ESG) | Ad Hoc Document Submission | 2026-06-27_Sustainability(_AdHoc_Legal.pdf | https://drive.google.com/file/d/DUMMY-108105/view | File Upload
2026-06-28 11:00 | Product & Website UI/UX (Product) | Ad Hoc Document Submission | 2026-06-28_Product&Website_AdHoc_Legal.pdf | https://drive.google.com/file/d/DUMMY-220465/view | File Upload
2026-06-29 09:00 | Human Resource | Quick Link & Asset Submission | Board Trello Sprint Planning V1 | https://www.figma.com/file/DUMMY-400814 | Quick Link
2026-07-02 14:00 | Product & Website UI/UX (Product) | Monthly Update | 2026-07-02_Product&Website_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-964749/view | File Upload
2026-07-02 16:00 | Product & Website UI/UX (Product) | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-726928/edit | Event Asset
2026-07-02 16:00 | Product & Website UI/UX (Product) | Event / Program Execution | Dokumentasi_Webinar Karir Digital_20260702 | https://drive.google.com/drive/folders/DUMMY-927564 | Event Asset
2026-07-05 16:00 | Administration & Performance Reporting | Ad Hoc Document Submission | 2026-07-05_Administration&_AdHoc_Report.pdf | https://drive.google.com/file/d/DUMMY-891615/view | File Upload
2026-07-06 12:00 | Administration & Performance Reporting | Ad Hoc Document Submission | 2026-07-06_Administration&_AdHoc_Knowledge.pdf | https://drive.google.com/file/d/DUMMY-380439/view | File Upload
2026-07-07 12:00 | Digital Marketing | Monthly Update | 2026-07-07_DigitalMarketin_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-579123/view | File Upload
2026-07-08 10:00 | Product & Website UI/UX (Website) | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-270128/edit | Event Asset
2026-07-08 10:00 | Product & Website UI/UX (Website) | Event / Program Execution | Dokumentasi_Sharing Session Alumni_20260708 | https://drive.google.com/drive/folders/DUMMY-971728 | Event Asset
2026-07-09 16:00 | Human Resource | Monthly Update | 2026-07-09_HumanResource_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-693419/view | File Upload
2026-07-10 15:00 | PR & Project Execution | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-836971/edit | Event Asset
2026-07-10 15:00 | PR & Project Execution | Event / Program Execution | Dokumentasi_Workshop CV & LinkedIn_20260710 | https://drive.google.com/drive/folders/DUMMY-777406 | Event Asset
2026-07-11 15:00 | Administration & Performance Reporting | Ad Hoc Document Submission | 2026-07-11_Administration&_AdHoc_Meeting.pdf | https://drive.google.com/file/d/DUMMY-440544/view | File Upload
2026-07-16 13:00 | Product & Website UI/UX (Website) | Monthly Update | 2026-07-16_Product&Website_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-805511/view | File Upload
2026-07-16 17:00 | PR & Project Execution | Monthly Update | 2026-07-16_PR&ProjectExecu_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-934816/view | File Upload
2026-07-18 11:00 | Product & Website UI/UX (Website) | Ad Hoc Document Submission | 2026-07-18_Product&Website_AdHoc_Contract.pdf | https://drive.google.com/file/d/DUMMY-470774/view | File Upload
2026-07-18 15:00 | Administration & Performance Reporting | Quick Link & Asset Submission | Board Trello Sprint Planning Update | https://www.figma.com/file/DUMMY-825686 | Quick Link
2026-07-19 15:00 | Product & Website UI/UX (Product) | Ad Hoc Document Submission | 2026-07-19_Product&Website_AdHoc_Legal.pdf | https://drive.google.com/file/d/DUMMY-914571/view | File Upload
2026-07-20 14:00 | Program Management Officer (PMO) | Quick Link & Asset Submission | Wireframe Figma Landing Page V2 | https://www.figma.com/file/DUMMY-868544 | Quick Link
2026-07-22 17:00 | Visual Brand Creative | Ad Hoc Document Submission | 2026-07-22_VisualBrandCrea_AdHoc_Contract.pdf | https://drive.google.com/file/d/DUMMY-449247/view | File Upload
2026-07-24 09:00 | Administration & Performance Reporting | Quick Link & Asset Submission | SOP Digital Onboarding V1 | https://www.figma.com/file/DUMMY-493124 | Quick Link
2026-07-25 09:00 | Program Management Officer (PMO) | Ad Hoc Document Submission | 2026-07-25_ProgramManageme_AdHoc_Legal.pdf | https://drive.google.com/file/d/DUMMY-632060/view | File Upload
2026-07-25 17:00 | Human Resource | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-244247/edit | Event Asset
2026-07-25 17:00 | Human Resource | Event / Program Execution | Dokumentasi_Sharing Session Alumni_20260725 | https://drive.google.com/drive/folders/DUMMY-180913 | Event Asset
2026-07-28 17:00 | PR & Project Execution | Quick Link & Asset Submission | Notion Knowledge Base Tim Batch 3 | https://www.figma.com/file/DUMMY-127965 | Quick Link
2026-07-30 16:00 | PR & Project Execution | Quick Link & Asset Submission | Master Design Feeds IG Batch 3 | https://www.figma.com/file/DUMMY-311383 | Quick Link
2026-07-31 11:00 | Product & Website UI/UX (Product) | Quick Link & Asset Submission | Master Design Feeds IG Batch 3 | https://www.figma.com/file/DUMMY-326130 | Quick Link
2026-07-31 12:00 | Human Resource | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-956572/edit | Event Asset
2026-07-31 12:00 | Human Resource | Event / Program Execution | Dokumentasi_Bootcamp Data Analyst Mini_20260731 | https://drive.google.com/drive/folders/DUMMY-940181 | Event Asset
2026-08-02 17:00 | Program Management Officer (PMO) | Ad Hoc Document Submission | 2026-08-02_ProgramManageme_AdHoc_Report.pdf | https://drive.google.com/file/d/DUMMY-108060/view | File Upload
2026-08-03 14:00 | Product & Website UI/UX (Website) | Quick Link & Asset Submission | Dashboard Notion Tracker Divisi Update | https://www.figma.com/file/DUMMY-731718 | Quick Link
2026-08-03 15:00 | PR & Project Execution | Ad Hoc Document Submission | 2026-08-03_PR&ProjectExecu_AdHoc_Knowledge.pdf | https://drive.google.com/file/d/DUMMY-624563/view | File Upload
2026-08-04 10:00 | Program Management Officer (PMO) | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-708519/edit | Event Asset
2026-08-04 10:00 | Program Management Officer (PMO) | Event / Program Execution | Dokumentasi_Webinar Karir Digital_20260804 | https://drive.google.com/drive/folders/DUMMY-571579 | Event Asset
2026-08-05 10:00 | Human Resource | Ad Hoc Document Submission | 2026-08-05_HumanResource_AdHoc_Legal.pdf | https://drive.google.com/file/d/DUMMY-721946/view | File Upload
2026-08-07 17:00 | Product & Website UI/UX (Website) | Quick Link & Asset Submission | Notion Knowledge Base Tim V1 | https://www.figma.com/file/DUMMY-766549 | Quick Link
2026-08-08 09:00 | Human Resource | Monthly Update | 2026-08-08_HumanResource_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-921273/view | File Upload
2026-08-08 09:00 | Product & Website UI/UX (Website) | Quick Link & Asset Submission | Folder Aset Kampanye Update | https://www.figma.com/file/DUMMY-101640 | Quick Link
2026-08-08 15:00 | Digital Marketing | Monthly Update | 2026-08-08_DigitalMarketin_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-616554/view | File Upload
2026-08-11 14:00 | Visual Brand Creative | Ad Hoc Document Submission | 2026-08-11_VisualBrandCrea_AdHoc_Report.pdf | https://drive.google.com/file/d/DUMMY-181644/view | File Upload
2026-08-12 10:00 | Digital Marketing | Ad Hoc Document Submission | 2026-08-12_DigitalMarketin_AdHoc_Knowledge.pdf | https://drive.google.com/file/d/DUMMY-185544/view | File Upload
2026-08-12 15:00 | Visual Brand Creative | Ad Hoc Document Submission | 2026-08-12_VisualBrandCrea_AdHoc_Meeting.pdf | https://drive.google.com/file/d/DUMMY-325583/view | File Upload
2026-08-12 16:00 | Human Resource | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-720148/edit | Event Asset
2026-08-12 16:00 | Human Resource | Event / Program Execution | Dokumentasi_Webinar Karir Digital_20260812 | https://drive.google.com/drive/folders/DUMMY-469038 | Event Asset
2026-08-13 12:00 | Human Resource | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-777513/edit | Event Asset
2026-08-13 12:00 | Human Resource | Event / Program Execution | Dokumentasi_Sharing Session Alumni_20260813 | https://drive.google.com/drive/folders/DUMMY-141043 | Event Asset
2026-08-13 14:00 | Product & Website UI/UX (Website) | Monthly Update | 2026-08-13_Product&Website_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-201255/view | File Upload
2026-08-16 13:00 | Administration & Performance Reporting | Monthly Update | 2026-08-16_Administration&_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-754644/view | File Upload
2026-08-17 11:00 | Program Management Officer (PMO) | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-187949/edit | Event Asset
2026-08-17 11:00 | Program Management Officer (PMO) | Event / Program Execution | Dokumentasi_Sharing Session Alumni_20260817 | https://drive.google.com/drive/folders/DUMMY-386042 | Event Asset
2026-08-18 14:00 | Sustainability (ESG) | Quick Link & Asset Submission | Dashboard Notion Tracker Divisi Batch 3 | https://www.figma.com/file/DUMMY-170966 | Quick Link
2026-08-19 09:00 | Program Management Officer (PMO) | Monthly Update | 2026-08-19_ProgramManageme_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-282710/view | File Upload
2026-08-19 11:00 | Product & Website UI/UX (Product) | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-659951/edit | Event Asset
2026-08-19 11:00 | Product & Website UI/UX (Product) | Event / Program Execution | Dokumentasi_Bootcamp Data Analyst Mini_20260819 | https://drive.google.com/drive/folders/DUMMY-424500 | Event Asset
2026-08-20 14:00 | Visual Brand Creative | Event / Program Execution | Detail Rincian Peserta | https://docs.google.com/spreadsheets/d/DUMMY-711046/edit | Event Asset
2026-08-20 14:00 | Visual Brand Creative | Event / Program Execution | Dokumentasi_Sharing Session Alumni_20260820 | https://drive.google.com/drive/folders/DUMMY-466813 | Event Asset
2026-08-20 17:00 | Product & Website UI/UX (Product) | Monthly Update | 2026-08-20_Product&Website_Laporan-Bulanan.xlsx | https://drive.google.com/file/d/DUMMY-339592/view | File Upload
2026-08-24 10:00 | Human Resource | Quick Link & Asset Submission | Wireframe Figma Landing Page V2 | https://www.figma.com/file/DUMMY-970720 | Quick Link